## Sheet1
Phase | Start Date | End Date | Duration (Days) | Progress (%) | Status | Tasks
Week 1: Data Collection And Exploration | 2025-02-05 | 2025-02-09 | 5 | 0 | Pending | Collect and clean loan data, Perform Eda, Handle missing values and outliners
Week2: Model Developement | 2025-02-10 | 2025-02-16 | 7 | 0 | Pending | Split data, Train logistic regression model, Tune hyperparametres using GridSearch, Cv - Evaluate model performance
Week3: Streamlit Interface Developement | 2025-02-17 | 2025-02-21 | 5 | 0 | Pending | Design UI layout ., Implement user input forms. , Integrate ML model into Streamlit
Week4: Database And Backend Integration | 2025-02-22 | 2025-02-27 | 6 | 0 | Pending | setup sql database for storing loan data, Connect Streamlit app with the databases
Week5: Testing And Optimization | 2025-02-28 | 2025-03-04 | 5 | 0 | Pending | Debug errors,, improve UI/UX , optimize model for better accuracy
Week6: Deployment And Documentation | 2025-03-05 | 2025-03-11 | 7 | 0 | Pending | Deploy on cloud server, Write project report, Final testing and user feedback